## Slide 1
Problem Statement
Schedule
  ANSRP Ecological Modeling Congressional Interest
Task | FY20 |  |  |  | FY21 |  |  |  | FY22 |  |  |  | FY23 |  |  | 
1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Current models cannot simulate nutrient flow across watershed scales, which prevents accurate prediction of how native and nuisance species will spatially distribute themselves across a landscape. Objective: Incorporate nutrient flow into the Gridded Surface Sub-surface Hydrologic Analysis (GSSHA) model and couple the nutrient model with ERDC's multi-species vegetation model.
Phase I. Water quality simulation capabilities (GSSHA-WQ)
Phase II. Integrated nutrient & vegetation simulation capabilities
Link the GSSHA-WQ with ERDC’s multi-species vegetation model for aquatic plants
Link the GSSHA-WQ with ERDC’s multi-species vegetation model for terrestrial plants
Complete/extend existing water temperature simulation capabilities in GSSHA for overland flow (runoff) & streams
  Temperature controls water quality kinetics rates
Link in-stream nutrient kinetics with GSSHA
  Nutrient Simulation Module (NSM) provides kinetics
Develop overland and sub-surface nutrient models
Technical Approach
Technical Approach Cont’d
Incorporating nutrient flow into overland flow and groundwater models to better predict ecological response across large scales Todd Steissberg (Todd.E.Steissberg@usace.army.mil, 530-574-5572)
Billy Johnson (LimnoTech), John Kucharski (EL), Charles Downer (CHL), Nawa Pradhan (CHL), Zhonglong Zhang (PSU), Lora Johnson (EL)

## Slide 2
Value statement for USACE operations
  ANSRP Ecological Modeling Congressional Interest
Forecasting Project Hurdles
Data exchange between models
Observed data for calibration/validation (flow, water quality, and vegetation)
  Use existing data, but may require travel in FY22-23
Budget by Q/Year
 | Qtr1 | Qtr2 | Qtr3 | Qtr4
FY20 | 0 | 25 | 125 | 150
FY21 | 75 | 75 | 75 | 75
FY22 | 75 | 75 | 75 | 75
Integrating nutrient flow with multi-species vegetation models will enable accurate simulation of native and nuisance species distribution across watersheds.
Next Steps
Example: Finish sensitivity tests 1Q FY22…
Incorporating nutrient flow into overland flow and groundwater models to better predict ecological response across large scales Todd Steissberg (Todd.E.Steissberg@usace.army.mil, 530-574-5572)
Billy Johnson (LimnoTech), John Kucharski (EL), Charles Downer (CHL), Nawa Pradhan (CHL), Zhonglong Zhang (PSU), Lora Johnson (EL)

## Slide 3
Successes/Results
Example: Leveraged ongoing projects to produce data…
  ANSRP Ecological Modeling Congressional Interest
Deliverable Tracking
  FY20: Contracts awarded, WQ development initiated
  FY21: GSSHA-WQ model capable of simulating overland and stream water temperature and nutrient flow; 4 technical notes
  FY22: GSSHA-WQ linked with aquatic plants model; 4 technical notes
  FY23: GSSHA-WQ linked with terrestrial plants model; final product; 4 technical notes
Incorporating nutrient flow into overland flow and groundwater models to better predict ecological response across large scales Todd Steissberg (Todd.E.Steissberg@usace.army.mil, 530-574-5572)
Billy Johnson (LimnoTech), John Kucharski (EL), Charles Downer (CHL), Nawa Pradhan (CHL), Zhonglong Zhang (PSU), Lora Johnson (EL)